## Sheet1
Date | Goal/Task | Responsible Person | Completed
June | Hold Organizational Meeting
Develop a Draft Budget
Develop a DRAFT timeline
Book Venue
Pavilion Lodge
Discuss Auto/Visual Needs with facility
Sign Contract for Hotel
July | Hold Committee Meeting
Begin Conference Agenda
Research Speakers
Research Break Out sessions
Review Awards
Discuss Social Events
Thursday Nite Dinner
Decide on venue
Confirm cost
Sign contract with facility
Get info to Marketing Committee
Friday Hospitality Night
Decide on Venue
Decide on Price for event
Decide on Max. Head count
Get info to Marketing Committee
Saturday Break Out Sessions
Decide on Venue
Confirm cost for rental/set up
Review AV needs/cost
Saturday Night Governor's Celebration
Decide on location
Organize layout
Review Electrical needs/cost
Menu and entertainment
Sunday Brunch
Decide on Venue
Confirm Cost for Rental/Meal
Transportation
Public Transportation - Boats to Island
Discuss Pricing with providers
Discuss Schedule with providers
Get cost and time schedules to Marketing Committee
Private boats/shipping
Develop list of boaters to assist
Coordinate schedule for transport needs
Child Care Activities
Develop DRAFT Activities
Confirm cost
Get info to Marketing committee
Family Events
Decide on activities
Marketing
Start Survey
Start Website
Social Media Conference Promotion
Layout DRAFT Video/s concepts
Develop DRAFT Sponsorship Package
August | Hold Committee Meeting
Conference Agenda
Tentative Speakers set
Refine Break Out sessions
Discuss Award needs
Marketing
Send out Survey
Finalize Website
Social Media Conference Promtion
Begin Production of Video/s
Refine Sponsorship Package
Signage at Conference
Review cost of Signage
Develop DRAFT Banner design
Develop DRAFT Directional Signs design
Transportation
Public Transportation - Boats to Island
Finalize Pricing with providers
Confirm Schedule with providers
Sign Any Necessary agreements
Get cost and time schedules to Marketing Committee
Private boats/shipping
Finalize list of boaters to assist
Coordinate schedule for transport needs
Child Care Activities
Complete DRAFT Activities outline
Confirm cost
Get info to Marketing committee
Family Events
Decide on activities
Sept | Conference Call Committee Meeting
Conference Agenda
Key note Speakers set
Other speakers?
Refine Break Out sessions
Discuss Award needs
Social Events
Draft Plan for Thursday Nite Dinner
Get info to Marketing Committee
Friday Night Hospitality
Confirm venue
Review of Lighting/Equipment Needs
Saturday Night Governors Celebration
DRAFT Plan Completed
Get info to Marketing Committee
Marketing
Report on Survey Progress
October | Hold Committee Meeting
Marketing
Finalize Website
Wrap Up Video/s
Develop Sponsorship Package
Print Sponsorship flyer/mailer
Coordinate Volunteers
Decide on number of volunteers needed
Pre-conference
Conference
Develop sign up sheet with times
Contact Rotaract to volunteer
Develop DRAFT Cash Security procedures
Nov | Hold Committee meeting
Begin Sponsorship Sales
December | DARK
January | Hold Committee meeting
Continue Sponsorship Sales
Secure two Silver Sponsors
Secure 4 Bronze Sponsors
Printing
Confirm Schedule of events
Start getting ads from Sponsors
Get List of Restaurants for attendees
Design 'Ask Me' T'-Shirts
Avalon Transportation
Cost of Shuttle/Taxi Service
Schedule of Service
February | Hold Committee Meeting
Continue Sponsorship Sales
Secure 4 Silver Sponsors
Secure 8 Bronze Sponsors
Secure 1 Gold Sponsor
Child Care Activities
Finalize Activities
Confirm cost
Get info to Marketing committee
Finalize All Transportation
Boats
Public
Private
March | Hold Committee meeting
Complete Sponsor Sales
Get final list to Marketing Committee
Marketing
Email out to Presidents
Visit clubs to promote
Launch website
Printing
Layout Programs for the Conference
Refine Conference Agenda
Speakers
Break Out sessions
Awards
Volunteers
Finalize Cash Accounting procedures
Finalize Volunteer List
April | Hold Committee Meeting
Marketing
Email out to Presidents
Visit final clubs to promote
Speakers
Confirm all speakers
Finalize printing
Programs
Signage
Posters
"As Me' t-shirts
Awards
Finalize awards
Hotel
Do final coordination
Hospitality booth
Meals
May | Hold Committee Meeting
Get final Headcount to hotel - meals/rooms
Volunteers
Confirm all volunteers
Finalize Volunteer Sign up Sheet
Thursday | Check In - Dinner
Set Up Volunteers - check in table
Set up check in table
Hand out Name tags
Print out Attendance list
Credit card machines
Friday, | Check In - On Island
Set Up Volunteer Greeters - at dock
Set Up Volunteers - check in table
Set up check in table
Hand out Name tags
Print out Attendance list
Set Up Credit card machines
Arrange Lost and Found
Saturday | Check In - On Island
Set Up Volunteer Greeters - at dock
Set Up Volunteers - check in table
Set up check in table
Hand out Name tags
Print out Attendance list
Set up Credit card machines
Arrange Lost and Found
Sunday | Wrap Up
Hold Breakfast
Pay Hotel Invoice
June | Hold Wrap Up meeting